## Names
TS_GS_ID | Agents Name | Status | Last Tested | Plan Start Date | Plan End Date | Code Implemented | Test Results | Remarks
1 | Sales Proposal Drafting Agent | ❌ Not Tested | - | 20/06/2025 | 20/06/2025 | No | No Agent Found Error | Awaiting fix
2 | Quotation Generator AI | ❌ Not Tested | 2025-11-07 20:42 | 20/06/2025 | 20/06/2025 | Yes | 100% Completed | Successfully validated output.
3 | Brand Visibility Insights Generator | ❌ Not Tested | 2025-11-07 20:43 | 20/06/2025 | 20/06/2025 | Yes | 100% Completed | Successfully validated output.
4 | Predict Leads Job Openings Agent | ❌ Not Tested | - | 20/06/2025 | 20/06/2025 | No | UI crashes | Awaiting fix
5 | 6 Hat Thinking Analysis | ❌ Not Tested | 2025-11-07 20:43 | 20/06/2025 | 20/06/2025 | Yes | 100% Completed | Successfully validated output.
6 | Zoom Call Icebreaker Agent | ❌ Not Tested | - | 20/06/2025 | 20/06/2025 | Yes | UI crashes | shows "100% Completed" but fails
7 | Conversion Rate Optimizer Agent | ❌ Not Tested | - | 20/06/2025 | 20/06/2025 | No | -
8 | Ultimate Personal Email Agent | ❌ Not Tested | - | 20/06/2025 | 20/06/2025 | No | -
9 | LinkedIn Profile Analyzer | ❌ Not Tested | 2025-11-07 20:46 | 21/06/2025 | 21/06/2025 | Yes | 100% Completed | Successfully validated output.
10 | LinkedIn Profile finder | ❌ Not Tested | 2025-11-07 20:44 | 21/06/2025 | 21/06/2025 | Yes | 100% Completed | Successfully validated output.
11 | LinkedIn Influencer PostMaker | ❌Not Tested | 2025-11-07 20:44 | 21/06/2025 | 21/06/2025 | Yes | 100% Completed | Successfully validated output.
12 | Loading Message Writer | ❌ Not Tested | 2025-11-07 20:45 | 21/06/2025 | 21/06/2025 | Yes | 100% Completed | Successfully validated output.
13 | YouTube to LinkedIn Post Generator | ❌ Not Tested | - | 21/06/2025 | 21/06/2025 | No | -
14 | YouTube to X Threads Agent | ❌ Not Tested | - | 21/06/2025 | 21/06/2025 | No | -
15 | Twitter Account Analyzer | ❌ Not Tested | - | 21/06/2025 | 21/06/2025 | No | -
16 | YouTube Channel Scraper | ❌ Not Tested | 2025-11-07 20:46 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
17 | AI Quiz Generator | ❌ Not Tested | 2025-11-07 20:47 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
18 | DISC Profile Generation Agent | ❌ Not Tested | 2025-11-07 20:47 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
19 | Ideal Customer Profile Tracker AI | ❌ Not Tested | 2025-11-07 20:48 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
20 | Instagram Profile Scraper Agent | ❌ Not Tested | 2025-11-07 20:48 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
21 | SEO Content Optimization | ❌ Not Tested | 2025-11-07 20:49 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
22 | Backlink Opportunity Finder | ❌ Not Tested | 22/06/2025 12:49:41 | 22/06/2025 | 22/06/2025 | Yes | 100% Completed | Successfully validated output.
23 | Web Page Copy Editor Agent | ❌ Not Tested | 2025-11-07 20:50 | 23/06/2025 | 23/06/2025 | Yes | 100% Completed | Successfully validated output.
24 | AI Prompt Improver Agent | ❌ Not Tested | 2025-11-07 20:51 | 23/06/2025 | 23/06/2025 | Yes | 100% Completed | Successfully validated output.
25 | Recruitment Workflow Agent | ❌ Not Tested | 2025-11-07 20:53 | 23/06/2025 | 23/06/2025 | Yes | 100% Completed | Successfully validated output.
26 | File Processing and Query Agent | ❌ Not Tested | - | 23/06/2025 | 23/06/2025 | No | Unauthorized error | Agent shows Unauthorized error
27 | Multi LinkedIn Search | ❌ Not Tested | 2025-11-07 20:54 | 23/06/2025 | 23/06/2025 | Yes |  | Exception: Expected condition failed: waiting for visibility of [[ChromeDriver: chrome on windows (5e527bce8f18c433cdbbc1f292bf8082)] -> xpath: //strong[contains(.,'100% Completed')]] (tried for 30 second(s) with 500 milliseconds interval)
28 | Website Analyzer and SWOT | ❌ Not Tested | 2025-11-07 20:55 | 23/06/2025 | 23/06/2025 | Yes | 100% Completed | Successfully validated output.
29 | Customer Persona Generator AI | ❌ Not Tested | - | 23/06/2025 | 23/06/2025 | No | No Agent Found Error | Awaiting fix
30 | Market Research Agent | ❌ Not Tested | - | 24/06/2025 | 24/06/2025 | No | No Agent Found Error | Awaiting fix
31 | Reddit Search Agent | ❌ Not Tested | 2025-11-07 20:55 | 24/06/2025 | 24/06/2025 | Yes | 100% Completed | Successfully validated output.
32 | ICP generator | ❌ Not Tested | - | 24/06/2025 | 24/06/2025 | No | -
33 | Dashboard Generator Agent | ❌ Not Tested | 2025-11-07 20:56 | 24/06/2025 | 24/06/2025 | Yes | 100% Completed | Successfully validated output.
34 | Tech Stack Lookup Agent | ❌ Not Tested | 2025-11-07 20:57 | 24/06/2025 | 24/06/2025 | Yes | 100% Completed | Successfully validated output.
35 | Storytelling B2B Sales Proposal Generator | ❌ Not Tested | 2025-11-07 20:58 | 24/06/2025 | 24/06/2025 | Yes | 100% Completed | Successfully validated output.
36 | CAC vs LTV Analysis Agent | ❌ Not Tested | 2025-11-07 20:58 | 24/06/2025 | 24/06/2025 | Yes | 100% Completed | Successfully validated output.
37 | Blog Post Outline Generator | ❌ Not Tested | 2025-11-07 20:59 | 25/06/2025 | 25/06/2025 | Yes | 100% Completed | Successfully validated output.
38 | LinkedIn Profile Insights Agent | ❌ Not Tested | 2025-11-07 21:00 | 25/06/2025 | 25/06/2025 | Yes | 100% Completed | Successfully validated output.
39 | Company Research Agent | ❌ Not Tested | - | 25/06/2025 | 25/06/2025 | No | No Agent Found Error
40 | Account Intelligence Agent | ❌ Not Tested | - | 25/06/2025 | 25/06/2025 | No | No Agent Found Error
41 | Competitive Ad Intelligence Agent | ❌ Not Tested | - | 26/06/2025 | 26/06/2025 | No | No Agent Found Error
42 | Partner Outreach Email Agent | ❌ Not Tested | 2025-11-07 21:01 | 26/06/2025 | 26/06/2025 | Yes | 100% Completed | Successfully validated output.
43 | Customer Onboarding Sequence Generator | ❌ Not Tested | 2025-11-07 21:02 | 26/06/2025 | 26/06/2025 | Yes | 100% Completed | Successfully validated output.
44 | Sales Call Script Generator Agent | ❌ Not Tested | 2025-11-07 21:03 | 26/06/2025 | 26/06/2025 | Yes | 100% Completed | Successfully validated output.
45 | Customer Testimonial Story Writer | ❌ Not Tested | 21/07/2025 18:24:50 | 26/06/2025 | 26/06/2025 | Yes |  | Exception: Expected condition failed: waiting for visibility of Proxy element for: DefaultElementLocator 'By.xpath: //strong[contains(.,'100% Completed')]' (tried for 30 second(s) with 500 milliseconds interval)
46 | Multichannel Outreach Planner Agent | ❌ Not Tested | - | 26/06/2025 | 26/06/2025 | No | - | Workflow failed error
47 | Ad A/B Test Analyzer Agent | ❌ Not Tested | 2025-11-07 21:05 | 26/06/2025 | 26/06/2025 | Yes |  | Exception: Expected condition failed: waiting for visibility of Proxy element for: DefaultElementLocator 'By.xpath: //strong[contains(.,'100% Completed')]' (tried for 30 second(s) with 500 milliseconds interval)
48 | Ad Audience Targeting Agent | ❌ Not Tested | 2025-11-07 21:07 | 27/06/2025 | 27/06/2025 | Yes | 100% Completed | Output successfully validated.
49 | Ad Performance Analyzer Agent | ❌ Not Tested | - | 27/06/2025 | 27/06/2025 | No | 100% Completed | Awaiting fix
50 | Affiliate Recruitment Agent | ❌ Not Tested | 2025-09-07 12:45 | 27/06/2025 | 27/06/2025 | Yes | 100% Completed | Output validated.
51 | Champion Identifier Agent | ❌ Not Tested | 2025-11-07 21:09 | 27/06/2025 | 27/06/2025 | Yes | 100% Completed | Successfully validated output.
52 | Content Repurposing Agent | ❌ Not Tested | 2025-11-07 21:09 | 27/06/2025 | 27/06/2025 | Yes |  | Exception: Expected condition failed: waiting for visibility of [[ChromeDriver: chrome on windows (5e527bce8f18c433cdbbc1f292bf8082)] -> xpath: //strong[contains(.,'100% Completed')]] (tried for 30 second(s) with 500 milliseconds interval)
53 | Employee Onboarding Assistant AI | ❌ Not Tested | - | 27/06/2025 | 27/06/2025 | No | 100% Completed | Awaiting fix
54 | Form Optimization Advisor | ❌ Not Tested | - | - | - | - | - | -
55 | GTM KPI Watchdog Agent | ❌ Not Tested | - | - | - | - | - | -
56 | Landing Page A/B Testing Agent | ❌ Not Tested | - | - | - | - | - | -
57 | Levo Email Finder Agent | ❌ Not Tested | - | - | - | - | - | -
58 | LinkedIn Page Analysis Agent | ❌ Not Tested | - | - | - | - | - | -
59 | Linkedin Recent Activity Finder Agent | ❌ Not Tested | - | - | - | - | - | -
60 | Meeting Scheduler Assistant | ❌ Not Tested | - | - | - | - | - | -
61 | Objection Handling Trainer Agent | ❌ Not Tested | - | - | - | - | - | -
62 | Outreach Sequence Optimizer Agent | ❌ Not Tested | - | - | - | - | - | -
63 | Partnership Opportunity Agent | ❌ Not Tested | - | - | - | - | - | -
64 | Pipeline Health Monitor Agent | ❌ Not Tested | - | - | - | - | - | -
65 | Product Recommendations Agent | ❌ Not Tested | - | - | - | - | - | -
66 | Product Requirements Document Agent | ❌ Not Tested | - | - | - | - | - | -
67 | Proposal Content Generator | ❌ Not Tested | - | - | - | - | - | -
68 | Sales Proposal Agent | ❌ Not Tested | - | - | - | - | - | -
69 | Search Query Analyzer Agent | ❌ Not Tested | - | - | - | - | - | -
70 | Persona Builder Agent | ❌ Not Tested | - | - | - | - | - | -
71 | Case Study Generator Agent | ❌ Not Tested | - | - | - | - | - | -
72 | Ad Campaign ROI Tracker Agent | ❌ Not Tested | - | - | - | - | - | -
73 | Deal Coaching Agent | ❌ Not Tested | - | - | - | - | - | -
74 | Lead Scoring Agent | ❌ Not Tested | - | - | - | - | - | -
75 | Lead Source Optimizer Agent | ❌ Not Tested | - | - | - | - | - | -
76 | Partnership Announcement Agent | ❌ Not Tested | - | - | - | - | - | -
77 | Partnership Co-Marketing Agent | ❌ Not Tested | - | - | - | - | - | -
78 | Prospect Research Agent | ❌ Not Tested | - | - | - | - | - | -
79 | Quota Attainment Tracker Agent | ❌ Not Tested | - | - | - | - | - | -
80 | Sales Funnel Conversion Analyzer | ❌ Not Tested | - | - | - | - | - | -
81 | Stock Market Analysis Agent | ❌ Not Tested | - | - | - | - | - | -
82 | Upsell Opportunity Agent | ❌ Not Tested | - | - | - | - | - | -
83 | Webinar Follow-up Email Writer | ❌ Not Tested | - | - | - | - | - | -
84 | Candidate Fit Analyzer | ❌ Not Tested | - | - | - | - | - | -
85 | Generate Cover Letter | ❌ Not Tested | - | - | - | - | - | -
86 | Intent Agent | ❌ Not Tested | - | - | - | - | - | -
87 | B2B Intelligence Agent | ❌ Not Tested | - | - | - | - | - | -
88 | Research Paper to Podcast Converter | ❌ Not Tested | - | - | - | - | - | -
89 | YouTube Thumbnail Generator Agent | ❌ Not Tested | - | - | - | - | - | -
90 | Partner Success Story Writer | ❌ Not Tested | - | - | - | - | - | -
91 | Influencer Partnership Outreach Agent | ❌ Not Tested | - | - | - | - | - | -
92 | Thought Leadership Article Writer | ❌ Not Tested | - | - | - | - | - | -
93 | Account Insights Summarizer | ❌ Not Tested | - | - | - | - | - | -
94 | Retargeting Campaign Generator | ❌ Not Tested | - | - | - | - | - | -
95 | Event Invite Outreach Agent | ❌ Not Tested | - | - | - | - | - | -
96 | LinkedIn Ads Copy Agent | ❌ Not Tested | - | - | - | - | - | -
97 | Research Paper Generator AI | ❌ Not Tested | - | - | - | - | - | -
98 | Slide Deck Outline Generator | ❌ Not Tested | - | - | - | - | - | -
99 | Social Media Post Generator Agent | ❌ Not Tested | - | - | - | - | - | -
100 | Win/Loss Analyzer Agent | ❌ Not Tested | - | - | - | - | - | -
101 | YouTube Video Scraper and Tweet Generator | ❌ Not Tested | - | - | - | - | - | -
102 | Marketing Copywriter Agent | ❌ Not Tested | - | - | - | - | - | -
103 | Regional Persona Profiler | ❌ Not Tested | - | - | - | - | - | -
104 | Territory Campaign Designer | ❌ Not Tested | - | - | - | - | - | -
105 | Ad Creative Idea Generator | ❌ Not Tested | - | - | - | - | - | -
106 | Influencer List Builder Agent | ❌ Not Tested | - | - | - | - | - | -
107 | Competitor Intelligence Agent | ❌ Not Tested | - | - | - | - | - | -
108 | Landing Page Copy Writer Agent | ❌ Not Tested | - | - | - | - | - | -
109 | Content Ideation Agent | ❌ Not Tested | - | - | - | - | - | -
110 | Testimonial Agent | ❌ Not Tested | - | - | - | - | - | -
111 | Hook Analyser Agent | ❌ Not Tested | - | - | - | - | - | -
112 | Hook Writer Agent | ❌ Not Tested | - | - | - | - | - | -
113 | TikTok Leads Hunter Agent | ❌ Not Tested | - | - | - | - | - | -
114 | Whitepaper Writer Agent | ❌ Not Tested | - | - | - | - | - | -
115 | Social Listening Agent | ❌ Not Tested | - | - | - | - | - | -
116 | X Post Generator Agent | ❌ Not Tested | - | - | - | - | - | -
117 | Trend Insight Agent | ❌ Not Tested | - | - | - | - | - | -
118 | Keyword Hunter Agent | ❌ Not Tested | - | - | - | - | - | -
119 | Candidate Profile Screening Agent | ❌ Not Tested | - | - | - | - | - | -
120 | Interview Question Generator Agent | ❌ Not Tested | - | - | - | - | - | -
121 | PESTLE Analysis | ❌ Not Tested | - | - | - | - | - | -
122 | Data Enrichment & Cleansing Agent | ❌ Not Tested | - | - | - | - | - | -
123 | A/B Test Results Analyzer | ❌ Not Tested | - | - | - | - | - | -
124 | KPI Dashboard Agent | ❌ Not Tested | - | - | - | - | - | -
125 | NPS Feedback Analyzer Agent | ❌ Not Tested | - | - | - | - | - | -
126 | Customer Health Tracker Agent | ❌ Not Tested | - | - | - | - | - | -
127 | Competitive Intelligence Summarizer | ❌ Not Tested | - | - | - | - | - | -
128 | Digital transformation ABM Agent | ❌ Not Tested | - | - | - | - | - | -
129 | 10k Scraper Agent | ❌ Not Tested | - | - | - | - | - | -
130 | Multi Linkedin Search | ❌ Not Tested | - | - | - | - | - | -
131 | Event ROI Forecaster | ❌ Not Tested | - | - | - | - | - | -
132 | Content Strategy Agent | ❌ Not Tested | - | - | - | - | - | -
133 | Sales Deck Tailor Agent | ❌ Not Tested | - | - | - | - | - | -
134 | LinkedIn Jobs Scraper Agent | ❌ Not Tested | - | - | - | - | - | -
135 | Ad Copy Generator Agent | ❌ Not Tested | - | - | - | - | - | -
136 | Paid Channel Allocator Agent | ❌ Not Tested | - | - | - | - | - | -
137 | Event Co-Sponsorship Planner | ❌ Not Tested | - | - | - | - | - | -
138 | Joint Webinar Planner Agent | ❌ Not Tested | - | - | - | - | - | -
139 | Partner Co-Marketing Planner | ❌ Not Tested | - | - | - | - | - | -
140 | Upsell Opportunity Identifier Agent | ❌ Not Tested | - | - | - | - | - | -
141 | Partnership Announcement Writer Agent | ❌ Not Tested | - | - | - | - | - | -
142 | Partner Tiering Analyst Agent | ❌ Not Tested | - | - | - | - | - | -
143 | Channel Partner Onboarding Assistant | ❌ Not Tested | - | - | - | - | - | -
144 | Partner Performance Tracker Agent | ❌ Not Tested | - | - | - | - | - | -

## Customer Health Tracker Agent
Health Status | Summary | Recommendation
Healthy | Customer engagement is consistent | Continue proactive support and engagement
At Risk | Drop in activity in last 30 days | Reach out with personalized check-ins
Critical | No login for 90 days | Escalate to account manager immediately

## Competitive Intelligence Summar
Target Company Name | Competitor Names | Focus Areas
Salesforce | HubSpot, Zoho, Freshworks | Marketing, AI Tools, CRM Features

## Sales Deck Tailor Agent
Account Name | Industry | Deal Stage | Personas | Pain Points | Additional Notes
Salesforce | SaaS | Discovery | VP of Sales, CFO, IT Decision Maker | Long sales cycle, difficulty in prospecting | Focus on enterprise-grade features

## Ad Copy Generator Agent
Product/Brand Name | Ad Platforms | Product Description
ChatMaster AI | Instagram | AI-powered chatbot for sales teams targeting SMBs

## CTA Optimiser Agent
CTA Goal | Tone | Target Persona | Context
Increase newsletter signups | Friendly, Urgent | Young professionals | Limited-time signup bonus offer

## Brand Voice Auditor Agent
Sales Text
Our eco-friendly water bottles are perfect for modern, health-conscious professionals who care about sustainability.

## Revenue Attribution Analyzer
Source | Campaign Name | Start Date | End Date
Google Ads | Summer Promo 2025 | 2025-07-01 | 2025-07-15

## Customer Feedback Agent
Company Name | Analysis Depth
Acme Corp | Executive-level analysis

## Industry Monitoring Agent
Industry Name | Region | Data Sources | Monitoring Frequency
Technology | North America | Gartner, IDC | Weekly
Healthcare | Asia | WHO, PubMed | Monthly

## Pitching Agent
Product Name | Tone | Product Description | Target Audience
SmartWatch X | Professional | A cutting-edge smartwatch with health tracking and AI features | Busy professionals & fitness enthusiasts

## Landing Page Copy Writer Agent
Landing Page URL
https://www.notion.so/product

## Content Ideation Agent
YouTube Channel Link | Keyword Query | Content Niche
https://www.youtube.com/@MattDAvella | productivity hacks, minimalism | Productivity & Personal Development
https://www.youtube.com/@GravityTransform | fat loss, muscle building | Fitness & Health
https://www.youtube.com/@GrahamStephan | investing, saving money | Personal Finance

## Testimonial Agent
Search Query | Time Filter | Result Limit
Notion for project management | Past month | 10

## TikTok Leads Hunter Agent
Search Keyword | Number of Posts | Country Code
music | 4 | AU

## Whitepaper Writer Agent
Topic | Target Audience | Tone | Length | Key Insights
Future of AI in BFSI | CXOs & Leaders | Professional | Long | Include trends, regulatory impacts, ROI insights, case studies

## Twitter X Post Generator
Topic | Target Audience | Brand Tone | Reference Content
AI in Startups | Startup founders | Witty | AI is changing how startups pitch to investors.

## Trend Insight Agent
Keywords | Limit
AI Trends | 20

## Keyword Hunter Agent
Article Text
Artificial Intelligence (AI) is transforming industries, from healthcare to finance, making processes smarter and more efficient.

## Interview Question Generator
Job Description
Looking for a Java Developer with strong skills in Spring Boot, REST APIs, SQL, and problem-solving.

## KPI Dashboard Agent
Report Title | Report Period | Department | Prepared By
Q2 Sales Performance | Q2 2024 | Sales | Pradeepthi

## Joint Webinar Planner Agent
Your Company Name | Partner Company Name | Key Talking Points | Webinar Format | Primary Goal | Target Audience | Your Company Strength | Partner Company Strength
DataPilot | TechSolutions | AI adoption in enterprisesFuture of ML | Panel Discussion | Build partnerships & generate new leads | CTOs, CIOs, Decision Makers | Expertise in workflow automation & ML | Strong client base in enterprise software

## SEO Content Strategy Agent
Business Website URL | Industry | Content Goals | Competitor URLs | Focus Topics | Target Audience Description
https://www.slack.com | SaaS | Increase traffic, Generate leads, Educate audience | https://www.gusto.com/ | HR software, onboarding, payroll | Mid-market HR leaders in tech, 200–1000 employees

## PR Monitoring Agent
Brand Name | Keywords | Channels | Language | Time Range
OpenAI | AI, ChatGPT, GPT | News | en | 24

## Email Writer Enricher Agent
Target Persona | Lead Name | Lead Job Title | Lead Company | Tone of Email | Company Website | Email Goal | Additional Context
VP of Marketing | John Smith | Marketing Director | Acme Inc. | Professional | https://acme.com | Introduce product | Lead has shown interest in AI tools

## Content Analysis Agent
Content Type | Target Audience | Primary Objective | Brand Voice | Content Body
Blog Post | Small business owners | Increase sign-ups | Professional, clear | Discover how our automation tools can save you hours and boost productivity.

## LinkedIn Content Engine Agent
Topics | Audience Type | Tone | Goal
Marketing, AI, SaaS | B2B Founders, Tech Professionals | Professional, Casual, Inspirational | Increase engagement, build brand authority, drive traffic

## Social Media Lead Generation
Keyword
AI in Healthcare

## Digital transformation ABM
Target Company | Company Name | Country
Tesla | Bilvantis | USA

## 10k Scraper Agent
Company Search | Form Types | Start Date | End Date | Pages to fetch
Apple Inc. | 10-K | 2023-01-01 | 2023-12-31 | 2

## Event ROI Forecaster
Event Name | Event Date | Event Location | Total Budget (INR) | Use Case | Audience Profile
Tech Summit 2025 | 2025-09-15 | Hyderabad | 500000 | Showcase AI product portfolio | CIOs, CTOs, IT Managers, Tech Enthusiasts

## LinkedIn Jobs Scraper Agent
LinkedIn Company URL
https://linkedin.com/company/microsoft

## Content Strategy Agent
Target Platforms | Tone | Business Goal | Audience Profile
LinkedIn, Blog | Professional | Increase qualified leads from LinkedIn for our HR software | HR managers in mid-sized tech companies

## Forecast Accuracy Tracker Agent
Forecast Name | Product / Business Area | Period to Analyze | Currency | Months | Forecast Values | Actual Values
Q3 Revenue Forecast | Subscription Sales | LAST_3_MONTHS | USD | Jan | 12000 | 11800

## Channel Partner Onboarding
Company Website URL
https://www.flipkart.com/

## Communication Strategist Agent
Target Audience | Topic | Tone | Social Media Platform
Tech-savvy Gen Z consumers | Sustainable fashion trends | Professional, Conversational | Instagram, LinkedIn, Twitter

## Company Research Agent
Company Name
Red Hat

## B2B_Intelligence_Agent
Column | Operator | Value | Data Type
First Name | contains | Netflix | Company Profile

## Account_Intelligence_Agent
Account Name | Target Persona | GTM Goal | Custom Notes
Adobe | VP of Marketing | book | This account recently raised Series B funding and is expanding its GTM team. They use HubSpot and Salesforce.

## LinkedIn_Profile_Insights_Agent
LinkedIn URL
https://www.linkedin.com/in/mukesh-kasimahanthi-8571a71ba/

## Blog_Post_Outline_Generator_Age
Blog Topic | Target Audience | Tone
How AI is transforming B2B marketing | B2B marketers, SaaS founders | Professional

## Generate_Cover_Letter
jobtitle | joblocation | experience
Data Scientist | Bangalore | 2 years

## ICP_generator
websiteurl
https://growstack.ai

## Dashboard_Generator_Agent
query
what is this pdf about?

## Tech_Stack_Lookup_Agent
websiteurl
https://growstack.ai

## Storytelling_B2B_Sales_Proposal
proddesc | audience
The Apple AirPods Pro (2nd Gen) are true wireless earbuds engineered for premium sound, advanced noise cancellation, and seamless integration with your Apple devices. Featuring the powerful H2 chip, these earbuds deliver richer audio with improved clarity and deeper bass. | People

## Competitive_Ad_Intelligence_Age
Competitor Name | Target Persona | Market | Objective
HubSpot | VP Marketing | SaaS | Lead Generation

## Partner_Outreach_Email_Agent
Partner Name | Partnership Type | LinkedIn Profile URL | Partnership Goal
Shopify | Co-marketing | https://linkedin.com/in/john-doe | Drive new customer acquisition through joint campaign

## CAC_vs_LTV_Analysis_Agent
Industry | Marketing Channel | CAC | ARPU | Customer Lifespan
SaaS | Google Ads | 250 | 400 | 12

## Customer_Onboarding_Sequence_Ag
username | company_name | role | subscription_plan | preferred_tone_dropdown | onboarding_goal_textarea
kumarmanoj707717@gmail.com | Bilvantis Technology | Senior Test Engineer | Pro | Formal , Friendly, Technical | Familiarize with the Organization/Project Environment Understand the company's culture, tools, workflows, and policies to align with the team and business objectives. Gain Access to Required Tools and Systems Ensure access to internal tools (e.g., Jira, Git, Slack, Confluence), test environments, repositories, and credentials. Understand the Role & Responsibilities Clearly define expectations, deliverables, key stakeholders, and scope of work for the onboarding individual. Start Contributing to Tasks Begin with small, low-risk tasks to gradually build confidence and understand the system in a hands-on way. Get Introduced to Team Members and Stakeholders Facilitate collaboration and communication by introducing the new member to relevant team members, managers, and cross-functional teams. Review Product Architecture or Business Process Study the technical documentation or business workflow to gain a functional and technical understanding of the system. Identify Training Needs Complete any mandatory training sessions (security, domain knowledge, tools, etc.) as part of the onboarding checklist.

## Influencer_Partnership_Outreach
Influencer Name | Influencer LinkedIn URL | Partnership Goal
Mukesh kasimahanthi | https://www.linkedin.com/in/mukesh-kasimahanthi-8571a71ba/ | Describe what you aim to achieve through this partnership

## Retargeting_Campaign_Generator
Product Name | platform | campaigngoal | tone | budget | offer | targetaudience
AI CRM Suite | Google | Convert free users to paid plan | professional | $2,000/month | 25% discount for first 3 months | Sales teams in SaaS startups looking to automate outreach

## Multichannel_Outreach_Planner_A
channels_checkbox | brandtone_field | Target Persona | Campaign Goal
Email, Linkedln, Twitter, Phone Call, SMS, Whatsapp | Friendly | Head of Marketting at a SaaS Company | Invite to webinar

## Event_Invite_Outreach_Agent
event_title | event_type | event_date | event_theme | target_persona | company_name | industry | call_to_action_goal | preferred_tone | outreach_channel
Scrum Call | Webinar | 2025-01-01 | Scaling B2B SaaS in 2025 | VP Of Meeting | Bilvantis Technology | Fintech | Register now | Professional | Email

## LinkedIn Ads Copy Agent
product_field | keywords_field | tone_dropdown | campaign_goal_dropdown | offer_field | call_to_action_field | target_audience_field
AI Agent | AI in testing | Professional | Lead Generation | 20% discount or free trial | Book a demo | Customer Support Teams (B2B & B2C) Businesses looking to automate repetitive support tasks and reduce response time. Ideal for industries like e-commerce, telecom, banking, and healthcare. Sales and Marketing Teams Teams aiming to use AI agents for lead qualification, automated follow-ups, and customer engagement. Helps improve conversion rates through smart, 24/7 AI-driven communication.

## Partner_Success_Story_Writer
partnername | industry | region | linkedinurl | problemdescription | solutiondescription
Acme Corp | Retail Technology | North America | https://linkedin.com/in/acmecorp | Struggled with customer retention and operational inefficiencies | Implemented AI-driven analytics and CRM integration

## GTM KPI Watchdog Agent
Analysis Query
Investigate the reason behind the drop in conversions in the last two weeks.

## Levo Email Finder Agent
LinkedIn URL | Name | Company Name
https://www.linkedin.com/in/prithvidamera | Prithvi Damera | redhat.com

## LinkedIn Page Analysis Agent
Company_linkedin_url
https://www.linkedin.com/company/growstack-ai/

## Linkedin Recent Activity Finder
Company_linkedin_url
https://www.linkedin.com/company/growstack-ai/

## Meeting Scheduler Assistant
Prospect Notes
Met with Sarah, VP of Marketing at Acme Corp. She's focused on improving lead quality and reducing CAC. Currently using HubSpot but struggling to personalize nurture flows. Recently lost a key account due to delayed outreach. Interested in AI-driven campaign automation and real-time scoring

## Objection Handling Trainer Agen
AE Persona | Topic | Objection Intensity | AE Response
Confident, consultative | Pricing, Timeline, Urgency | High | I completely understand your concern around pricing. Let’s focus on the long-term value here—our solution reduces manual effort by over 40%, saving costs overall. I’m happy to walk you through a flexible plan that aligns with your budget and timeline.

## Outreach Sequence Optimizer Age
Current Outreach Sequence | Target Audience | Outreach Goal | Preferred Channel | Company Name | Product Description
1. Subject: Boost engineering productivity Body: Hi [Name], I noticed your team is growing fast. Our AI workflow builder helps tech teams automate repetitive tasks and speed up releases by 30%. Interested in a quick chat? 2. Follow-up: Just checking in—any interest in automating workflows to give your team back valuable dev hours? | Startup CTOs | Book a meeting | Email | Acme Corp | An AI-powered workflow automation platform that helps engineering teams reduce manual tasks and speed up delivery.

## Landing Page AB Testing Agent
Variant A URL | Variant B URL | Variant A Visits | Variant A Signups | Variant A Avg Time Spent | Variant B Visits | Variant B Signups | Variant B Avg Time Spent
https://acme.com/landing-a | https://acme.com/landing-b | 500 | 30 | 25.5 | 500 | 45 | 31

## Partnership Opportunity Agent
Your Company URL | Target Company URL
https://acmeai.com | https://growthstacklabs.com

## Pipeline Health Monitor Agent
Analysis Query
What stages in the sales funnel are causing the most drop-offs over the last quarter?

## Proposal Content Generator
Client Name | Project Name | Deadline | Budget | Project Goal | Services to Include | Key Challenges
ACME Corp | Website Redesign | 2025-08-31 | $10,000 – $15,000 | Redesign ACME's corporate website to improve user experience, mobile responsiveness, and lead capture | UI/UX design, front-end development, CMS integration, SEO optimization | Tight timeline, need to preserve existing SEO rankings, multiple stakeholder approvals required

## Search Query Analyzer Agent
search_query_field
Best Automation testing tools in the market

## Slide Deck Outline Generator
ContentType | Tone/Style | Campaign Goals | Audience Persona | Product Summary | Key Messaging
Webinar | Professional | Increase product awareness among healthcare professionals | Indian healthcare practitioners in Tier 2/3 cities | Growstack.ai's Aigent is a no-code platform to create, deploy, and monetize AI agents across web, voice, and social platforms. | Launch AI agents in minutes, no coding required; automate support, sales & marketing; agents with memory; monetize via tokens/subscriptions; deploy across multiple channels.

## Social Media Post Generator
main message textarea
AI in automation testing

## Product Recommendations Agent
Product Query
What are the best budget laptops under ₹50,000 for remote work and video calls?

## Sales_Call_Script_Generator_Age
leadname | companyname | leadrole | industry | callgoal
John Doe | Acme Corp | Head of Sales | Retail Technology | Schedule a demo, explore collaboration

## Customer_Testimonial_Story_Writ
Desired Tone | Raw Customer Feedback
Inspiring | We've been using the product for six months, and it's completely changed the way we manage our workflow. Our team is more productive, and customer satisfaction has improved significantly.

## Thought_Leadership_Article_Writ
Article Topic | Target Audience | Tone of Voice
Future of AI in Business Operations | SaaS founders | Professional

## Event Co-Sponsorship Planner
Event Type | Event Date | Location | Total Budget (INR) | Host Resources | Co-Sponsor Budget (INR) | Co-Sponsor Capabilities | Co-Sponsor Expectations | Event Goals
Tech Conference | 2025-09-30 | Bengaluru | 150000 | Venue, Equipment | 50000 | Speaker Access, Reach | Logo placement, speaker slot | Build brand awareness, generate leads

## Partnership Announcement Writer
Company A Domain | Company B Domain | Contact Email for Press Inquiries | Nature of Partnership
microsoft.com | adobe.com | press@partnernews.com | Strategic collaboration in AI marketing

## Influencer List Builder Agent
Campaign Topic | Budget ($) | Product Details | Additional Info
Fitness Gear | 5000 | High-end smart fitness wearable device | Targeting US & UK, Instagram & YouTube influencers

## Loading Message Writer
Company | Website URL
Growstack Inc | https://growstack.ai

## Reddit Search Agent
Time Filter | No of Posts | Search Query
All time | 2 | AI tools for productivity
Past week | 2 | startup funding stories

## Market Research Agent
Industry
Fintech
EdTech

## Customer Persona Generator AI
Demographic and Psychographic Details
Female, Age 25-34, working professional, lives in urban India, interested in tech & fitness, goal-oriented

## YouTube Thumbnail Generator
YouTube Video URL | Video Title | Number of Thumbnails
https://www.youtube.com/watch?v=2khkzhgC2wU | Pachi Mosam Jara Jagratha | 1

## Website Analyzer and SWOT
Your Website URL | Competitor Website URL
https://www.youtube.com/ | https://www.youtube.com/

## Multi Linkedin Search
First Name | Last Name | Company | Email | Country
Niharika | Niha | Google | example@gmail.com | india

## Intent Agent
URL
https://www.linkedin.com/in/sai-bramarambika-bonagiri/

## Candidate_Fit_Analyzer
URL | Job Description
https://www.linkedin.com/in/sai-bramarambika-bonagiri/ | About the job Script Assist is building the operating system for the future of private healthcare. Already powering over 20% of the UK’s medical cannabis market and now expanding fast into next-gen therapies like GLP-1s and TRT, we’re the backbone behind digital clinics and pharmacies transforming patient care. With month-on-month growth above 15% and a team obsessed with impact, we’re reinventing how healthcare works—making it faster, safer, and smarter for everyone. Build Something That Actually Matters Are you ready to code for impact? At Script Assist, you won’t just be moving tickets—you’ll be building mission-critical features that help real doctors, clinics, and patients in one of the world’s fastest-growing healthtech markets. Here, every line of code you ship directly powers better care, safer medicines, and a smarter healthcare system. If you want a job where you see your skills matter every day—and where your stack expertise gets used, tested, and celebrated—keep reading. What You’ll Do Build and maintain scalable backend systems in NodeJS, NestJS, and TypeScript. Design, implement, and optimize RESTful APIs powering a complex, multi-tenant health platform. Deliver modern, high-quality user experiences in ReactJS (with TypeScript)—not just pixel-pushing, but real feature work. Work across the stack to solve problems, ship features, and squash bugs fast. Collaborate with a high-energy product and engineering team who genuinely care about code quality and user impact. Write tests, review code, and help us keep our standards world-class. Dive into new technologies—if there’s a better way, help us find it. Make healthcare smarter, safer, and more human—one release at a time. What We’re Looking For 2-4 years’ experience as a full stack or backend developer. Solid hands-on with NodeJS, NestJS, TypeScript—you know your way around scalable APIs and modern backend design. At least 2 years building with ReactJS (TypeScript preferred) on real-world projects. Comfortable with PostgreSQL or MongoDB, data modeling, and integrating with external APIs. Fluent English, excellent communication, and a collaborative, get-things-done approach. Passion for innovation and building products that make a difference. Bonus: You’ve worked on SaaS, healthcare, or other complex, regulated platforms. Why Script Assist? Your code saves lives. You’ll see real-world impact, not just vanity metrics. Learn fast, grow faster. This is a high-performance team with big ambitions—and no dead weight. Full-stack, full ownership. We don’t do silos. You’ll see projects through from API to UI. Be part of something bigger. We’re a close-knit, remote-friendly team building healthcare’s next backbone

## File Processing and Query Agent
Query
Brief me about this file in two paragraphs

## Recruitment Workflow Agent
Skills | Experience
react, javascript | 5

## Backlink Opportunity Finder
Technology
Artificial Intelligence

## Web Page Copy Editor Agent
Website_URL
https://www.apple.com/in/macbook-air/

## AI Prompt Improver Agent
Initial Prompt
Write an essay about climate change.

## SEO Content Optimization
Website URL | Content Text
https://www.example.com/about | We are an AI-driven SaaS company optimizing business intelligence with advanced analytics and machine learning solutions tailored for enterprises.

## Instagram Profile Scraper Agent
Profile Username
tejaswinimanogna

## Ideal Customer Profile Tracker
Customer Data
Samantha Lee, Salesforce Arjun Mehta, Infosys Natalie Gomez, Adobe

## DISC Profile Generation Agent
LinkedIn Profile URL
https://www.linkedin.com/in/sai-bramarambika-bonagiri/

## AI Quiz Generator
Exam Type | Topic | Difficulty Level
GRE | Reading Comprehension | Medium

## YouTube Channel Scraper
YouTube Channel URL
https://www.youtube.com/@MrBeast

## YouTube Video Scraper and Tweet
YouTube URL
https://www.youtube.com/watch?v=OqYXuLQJdZY

## Twitter Account Analyzer
Twitter handle | twitter profile url
swapCod | https://x.com/swapCod

## YouTube to X Threads Agent
YouTube URL
https://www.youtube.com/watch?v=OqYXuLQJdZY

## LinkedIn Influencer PostMaker
Influencers LinkedIn Profile URL | Topic of the Post
https://www.linkedin.com/in/satyanadella/ | How Generative AI is Transforming the Future of Work

## Account Insights Summarizer
Account ID | Account Name | Company Domain
ACC-12345 | Acme Corp | acme.com

## Persona Builder Agent
Marketing Goal | Your Business Details | Target Audience Details
Generate leads | Growstack.ai is a SaaS company offering a no-code AI agent platform that enables businesses to build, deploy, and monetize AI agents across channels. | Mid-level to senior decision-makers (Marketing, Operations, Product) in tech startups and mid-sized SaaS firms globally.

## Case Study Generator Agent
Selected Title | Customer Background | Product Usage | Customer Quote
How Acme Health Automated Patient Support with Growstack.ai | Acme Health is a mid-sized healthcare provider in India, serving 10,000+ patients monthly. They struggled with slow response times and high call center costs. | Acme used Growstack.ai’s no-code AI agent to handle FAQs, appointment scheduling, and post-visit follow-ups via WhatsApp and web chat. | “Growstack.ai helped us reduce patient query time by over 60% while improving satisfaction across channels.”

## Ad Campaign ROI Tracker Agent
Campaign Period | Primary KPI | Target ROAS | Target CPA | Target CTR | Custom Notes
Q2 2025 | ROAS | 4 | 250 | 2.5% | Focus on performance across LinkedIn and Google Ads campaigns targeting APAC.

## Deal Coaching Agent
Deal Name | Deal Stage | Deal Amount | Expected Close Date | Last Activity Date | Interaction Count | Primary Contact Name | Primary Contact Role | Recent Notes
Acme AI Rollout | Negotiation | 25000 | 2025-08-15 | 2025-07-25 | 4 | Sarah Verma | CTO | Client asked for revised pricing. They are evaluating internally and considering a competitor.

## Lead Scoring Agent
LinkedIn Profile URL | Lead Industry | Lead Role | Company Size | Region | Email Sent | Reply Received
https://linkedin.com/in/sarah-verma | SaaS | CTO | 50 | North America | Hi Sarah, we help tech teams streamline operations with AI agents. Would love to show you a quick demo if you're exploring automation tools. | Thanks for reaching out. We're currently evaluating options and may consider automation later this quarter. Please follow up in 2 weeks.

## Stock Market Analysis Agent
Stock Ticker Symbol | Financial Inquiry
TSLA | What was Tesla’s net income in the last quarter?

## Upsell Opportunity Agent
Customer ID | Company Domain | Stock Symbol
CUST12345 | acmecorp.com | AAPL

## Partnership Co-Marketing Agent
Partner Domain | Marketing Goals | Campaign Plans
https://growthstacklabs.com | Increase shared brand visibility, generate leads, and drive joint webinar attendance | Launch a joint webinar series, co-branded blog content, LinkedIn ads targeting shared ICP, and a cross-promotional newsletter

## Webinar Follow-up Email Writer
Attendee Full Name | Webinar Title | Webinar Date | Speaker Name | Key Takeaways | Attendee's Job Title | Call to Action
Manoj Kumar Behera | AI in Automation Testing | 2025-08-15 | Niharika Bandila | Functional testing, use cases, advantages, disadvantages | Senior Test Engineer | Watch the recording

## Sales Funnel Conversion Analyze
Company Domain | Company Name
growstack.ai | Growstack Technologies

## Prospect Research Agent
Company Domain | Company Name
growstack.ai | Growstack Technologies

## Lead Source Optimizer Agent
HubSpot Access Token
pat-eu1-5d8f3c9e-4f8d-4acb-92a1-xxxxxxx

## Partnership Announcement Agent
Company A Domain | Company B Domain | Contact Email for Press Inquiries | Nature of Partnership
microsoft.com | adobe.com | press@microsoft.com | Microsoft and Adobe are partnering to integrate Adobe Sign with Microsoft Teams, enabling seamless document workflows and secure e-signatures within the Teams environment.

## Ad AB Test Analyzer Agent
Test Name | Platform | Goal | Start Date | End Date | Variant A Name | A Impressions | A Clicks | A Conversions | A Spend | Variant B Name | B Impressions | B Clicks | B Conversions | B Spend
Summer Campaign | Facebook | Maximize Conversions | 2025-01-07 | 15-07-2025 | Variant A | 10000 | 850 | 120 | 500 | Variant B | 9500 | 800 | 130 | 450

## Ad Performance Analyzer Agent
Platform | Campaign Objective | Ad Content
Facebook | Lead Generation | Discover the easiest way to grow your leads—get started today with our all-in-one solution!

## Affiliate Recruitment Agent
Niche | Target Platforms | Max Number of Leads | Affiliate Link | Commission Structure | Brand Name | Custom Affiliate Message
Skincare | Instagram | 10 | https://glowupskincare.com/signup | 15% per sale | GlowUp Skincare | We'd love to collaborate with you! Join our skincare affiliate team.

## Ad Audience Targeting Agent
Campaign Objective | Target Market Industry | Target Market Company Size | Target Market Location | ICP Title Keywords | ICP Pain Points | Competitor Brands | Platforms | Product Description
Drive signups | SaaS | 51–200 | United States | Marketing Manager, Growth Lead | Low conversion, high CAC | HubSpot, Salesforce | LinkedIn, Google, Meta | An all-in-one CRM for growing B2B startups.

## Champion Identifier Agent
Account ID | Account Name | Email Threads | Meeting Transcripts | CRM Activities | Participants
ACC-789 | FutureTech Inc. | [{"subject": "Q3 Strategy Discussion", "from": "alice@futuretech.com", "to": "rep@salescrm.com", "timestamp": "2025-07-01T10:00:00Z"}] | [{"meeting_title": "Product Demo", "transcript": "Alice asked multiple questions about integration features..."}] | [{"type": "Call", "note": "Follow-up call with Alice on pricing", "date": "2025-07-03"}] | [{"name": "Alice Johnson", "role": "Director of Marketing"}, {"name": "Bob Lee", "role": "CTO"}]

## Content Repurposing Agent
Output Formats | Tone | Audience | Platform Style | Additional Instructions | Research Content
LinkedIn, Twitter, Blog | Insightful | Founders, Marketers | Twitter threads, LinkedIn posts | Highlight stats and make it engaging for social sharing | AI is transforming the way businesses approach lead generation, customer service, and data analysis. In this guide, we’ll explore how automation is scaling SaaS operations...

## Employee Onboarding Assistant A
Company Name | Question
Growstack.ai Pvt. Ltd | What documents do I need to submit before my first day of joining?

## Form Optimization Advisor
Form Topic | Frontend Framework | HTML Form Code
Lead Gen | HTML | <form><input type="text" placeholder="Name"><input type="email" placeholder="Email"><button>Submit</button></form>

## Sales Proposal Agent
lead_full_name_field | lead_industry_field | lead_email_field | lead_linkedin_account_link_field | sender_details_textarea | business_details_textarea
Manoj Kumar Behera | Information Technology | kumarmanoj707717@gmail.com | https://www.linkedin.com/in/manojkubehera/ | Manoj Kumar BeheraSenior Test EngineerBilvantis Technology | Business Name: Growstack.ai Pvt. Ltd.Business Type: Private Limited CompanyIndustry: Artificial Intelligence & SaaS SolutionsBusiness Description:Growstack.ai is a technology company specializing in AI-powered business automation tools and SaaS platforms. We help startups and enterprises optimize operations, improve decision-making, and scale efficiently through smart digital solutions.Address:3rd Floor, Orion Tech Park, HSR Layout, Bengaluru, Karnataka – 560102Contact:📞 +91 91234 56789✉️ support@growstack.ai🌐 www.growstack.aiDate of Incorporation: 12-Feb-2022CIN: U72900KA2022PTC123456GSTIN: 29ABCDE1234F1Z5Key Personnel:Founder & CEO: Mr. Arjun MalhotraHead of Engineering: Ms. Kavya IyerSocial Media:LinkedIn: linkedin.com/company/growstackaiTwitter: twitter.com/growstack_ai

## Ultimate Personal Email Agent
LinkedIn Profile URL
https://www.linkedin.com/in/sai-bramarambika-bonagiri/

## YouTube to LinkedIn Post Gen
YouTube Video URL
https://www.youtube.com/watch?v=3bxYkBVzcmw

## LinkedIn Profile Analyzer
Target LinkedIn Profile URL
https://www.linkedin.com/in/sai-bramarambika-bonagiri/

## Conversion Rate Optimizer Agent
Business_Domain | Industry | Business_goal
amazon.com | eCommerce | improve user sign ups

## Zoom Call Icebreaker Agent
Your LinkedIn Profile | Other Persons LinkedIn Profile
https://www.linkedin.com/in/sai-bramarambika-bonagiri/ | https://www.linkedin.com/in/saireddy0annamareddy/

## LinkedIn Profile Finder
First Name | Last Name | Company Name
Sai Bramarambika | Bonagiri | Growstack Inc.

## Predict Leads Job Openings
Company_Domain | Job_Title | Location | Remote_Type
microsoft.com | Data Analyst | India | Full Time

## 6 Hat Thinking Analysis
Idea Description
An AI-powered mobile app called MediScan AI that allows users to take pictures of visible symptoms (e.g., rashes, eye redness, wounds) and get an instant preliminary health analysis. The app uses a computer vision model trained on medical datasets and integrates with a chatbot to provide follow-up suggestions like doctor recommendations, home remedies, or urgency flags. It's aimed at remote areas with limited healthcare access.

## Research Paper Generator AI
Topic or Question
Impact of Artificial Intelligence on Employment in India

## Brand Visibility_03
Brand Name
Google
Samsung

## Sales_Proposal_Drafting_Agent
name | industry | linkedin | senderDetails | businessDetails
Sai Bramarambika Bonagiri | IT Services | https://www.linkedin.com/in/sai-bramarambika-bonagiri/ | Social Media Marketing Specialist | We offer cloud solutions

## Quotation Generator AI
LinkedIn Url | Business Offerings | Business Details
https://www.linkedin.com/in/sai-bramarambika-bonagiri/ | Cloud Hosting - ₹2,999/month | GrowStack Technologies Pvt. Ltd., 5th Floor, Cyber Towers, Madhapur, Hyderabad, Telangana - 500081, Phone: +91-9876543210, Email: contact@growstack.ai